# Martha’s Strategic Plan — Aging Transitions Workshop

Prepared by: Martha Date: 2026-05-14 16:34 For: Clark Johnson (PI) Status: Accepted Re: Project roadmap and session agenda

## Phase 1 — Project Setup [COMPLETE]

Define project purpose, establish team roster, build folder structure, write infrastructure files, configure session hook. ✓ Done Session 1.

## Phase 2 — Content Development [NEXT]

Develop the substantive content for each of the three gap areas the workshop addresses.

Session agenda items:

2a. HIPAA Gap Analysis - HIPAA Advisor produces: analysis of HIPAA’s practical barriers for aging support networks; what authorizations exist; what participants can do at the workshop - Output: memo for Martha and Clark; input to Content/ and Templates/

2b. Sudden Incapacity Gap Analysis - HIPAA Advisor + Workshop Planner: map the sudden-incapacity scenario — who should know what, what systems fail, what preparation addresses the gap - Output: content memo; input to presentation outline

2c. Slow Decline Gap Analysis - Workshop Planner + HIPAA Advisor: identify trigger criteria frameworks; caregiver recognition challenges; resource navigation gaps (especially when insurance is limited) - Output: content memo; input to presentation outline

## Phase 3 — Resource Inventory [NOT STARTED]

Librarian catalogs what actually exists on Lopez Island and San Juan County.

Session agenda items:

3a. Lopez Island Senior Services Survey - Librarian: catalog Senior Center services, Home Care agency offerings, library programs, clinic services - Categories: home care, transportation, financial assistance, insurance navigation, mental health, caregiver support

3b. San Juan County and Regional Resources - Librarian: services accessible by ferry or remotely (Anacortes, telehealth, state programs) - Flag gaps where island isolation creates unmet need

## Phase 4 — Workshop Design [NOT STARTED]

Workshop Planner designs the full event architecture.

Session agenda items:

4a. Session Flow and Agenda - Morning and afternoon sessions timed and sequenced - Presentation slots, breakout group structure, activity session design - Facilitator guide for each segment

4b. Completeness Review - Workshop Planner assesses: can this workshop be delivered “out of the box”? - What is missing? What needs to be prepared in advance? - Identify any single points of failure

## Phase 5 — Participant Materials [NOT STARTED]

Writer produces all participant-facing documents.

Session agenda items:

5a. Promotional Flyer - Writer: one-page flyer for library distribution and partner promotion - Audience: general Lopez Island public; tone: welcoming, practical, not alarming

5b. Action Plan Template - Writer: individualized participant template — sections for each gap area; fillable at the workshop - HIPAA Advisor reviews for accuracy on authorization sections

5c. Resource Guide - Writer (from Librarian inventory): formatted Lopez Island resource guide - Organized by category; practical contact info and access notes

## Phase 6 — Partner Coordination [NOT STARTED]

Engage partner organizations for content review and logistics confirmation.

Session agenda items:

6a. Partner Review Package - Martha: assemble review package for Senior Center, Home Care org, library, clinic - Request: content accuracy feedback; local knowledge additions; logistics confirmation

6b. Incorporate Partner Feedback - Update materials based on partner input

## Phase 7 — Final Review [NOT STARTED]

7a. Workshop Planner Final Completeness Check - All materials complete and consistent - Facilitator prepared; contingencies identified

7b. Clark Final Approval - Clark reviews all participant-facing materials before delivery

## Completed Sessions

| Session | Date | Phase Item |
| --- | --- | --- |
| 1 | 2026-05-14 | Phase 1 — Project Setup |